## Yes please!
Week | Task Description | Primary Owner | Deliverables / Output
Week 5 | Database schema setup & authentication foundation | Sakshi & Anthony | PostgreSQL tables, Firebase Auth middleware, pgvector binaries installed
Week 5 | Requirements alignment & test plan drafting | Prathyusha | Test strategy document, updated project schedule tracking
Week 6 | Health metrics ingestion & Gemini embedding service | Sakshi & Anthony | POST/PUT /api/v1/metrics endpoints, embeddingService.js (768-dim)
Week 6 | Metric API test cases & initial validation | Prathyusha | Postman test suites for metrics and auth routes
Week 7 | Health goals dashboard & semantic search engine | Sakshi & Anthony | Health dashboard UI backend support, cosine similarity search via pgvector
Week 7 | API documentation & evidence collection | Prathyusha | Postman collection exports, API testing screenshot evidence
Week 8 | System architecture docs & PR consolidation | Sakshi & Anthony | Data flow diagrams, PR #35 & PR #47 merges into main
Week 8 | Progress Report 2 compilation & meeting minutes | Prathyusha | Consolidated Excel tracking sheet, meeting minutes review (Weeks 5–8)