Table 1 Task Dependencies

| Task | Effort (hours) | Duration (days) | Dependencies |
| --- | --- | --- | --- |
| T1: Finalise requirements & design | 15 | 7 |  |
| T2: Environment & tool setup | 8 | 4 |  |
| T3: UI/UX wireframes (Figma) | 10 | 5 | T1 (M1) |
| T4: DB schema design | 6 | 4 | T1 (M1) |
| T5: Backend API scaffolding | 10 | 6 | T4, T2 |
| T6: Auth implementation | 8 | 5 | T5 (M2) |
| T7: Data integration module | 12 | 7 | T5 (M2) |
| T8: Recommendation engine (GenAI) | 20 | 10 | T5 (M2), T2 |
| T9: Chatbot module | 15 | 8 | T5 (M2), T2 |
| T10: Mental health module | 12 | 6 | T2 |
| T11: Notifications | 6 | 3 | T5 (M2), T2 |
| T12: Frontend screens (all) | 25 | 12 | T3, T6 (M3) |
| T13: Integration & testing | 20 | 8 | T7, T8, T9, T10, T11, T12 (M4) |
| T14: Documentation & report writing | 15 | 7 | T13 (M5) |
| T15: Presentation prep | 6 | 3 | T14 |

M1 is the milestone associated with completion of task T1 (requirements finalised).

M2 is the milestone associated with completion of task T5 (core backend API ready).

M3 is the milestone associated with completion of tasks T3 and T6 (UI wireframes and authentication ready).

M4 is the milestone associated with completion of tasks T7, T8, T9, T10, T11 and T12 (all subsystems and frontend feature-complete).

M5 is the milestone associated with completion of task T13 (integration testing complete).