## Overview
AI-Powered Personal Health Assistant
COIT20273 Capstone Project — Team Plan (Week 1)
Team roster
Name | Subsystem(s) owned | Role | Current status
Anthony | Recommendation engine subsystem | Team leader (Weeks 1-4) | Active
Sakshi | User management + Data integration subsystems | Team member | Active
Prathyusha | Chatbot + Mental health subsystems | Team member | Active
Legend
Yellow-filled cells | Update these as the project progresses (status, owners, dates)
Note | Weekly activities are working documents for your team — no submission needed until the formal assignment later in term.

## Anthony
Anthony's tasks
Team leader for Weeks 1-4
Subsystem owned: | Recommendation engine subsystem (diet plans, exercise plans, health dashboard)
Task | Due | Status
Run and chair the Week 1 team meeting; consolidate outputs for tutor consultation | This week | Not started
Finalise the project scope wording with team input | This week | Not started
Set up the shared repo / workspace (GitHub, Trello, etc.) | This week | Not started
Confirm the GenAI API to use (e.g. OpenAI, Claude API) for recommendations | Before Week 2 | Not started
Draft functional requirements for: view health dashboard, get diet recommendation, get exercise recommendation | Before Week 2 | Not started
Research prompt design approaches for generating diet/exercise plans | Before Week 2 | Not started

## Sakshi
Sakshi's tasks
Team member
Subsystem owned: | User management subsystem + Data integration subsystem
Task | Due | Status
Draft functional requirements for: register/manage profile, set health goals, sync wearable data | Before Week 2 | Not started
Research wearable data sources (Fitbit, Google Fit, Apple Health APIs) and recommend simulated dataset approach | Before Week 2 | Not started
Define the user profile data model (age, weight, goals, dietary needs, etc.) | Before Week 2 | Not started
Identify privacy/data-handling considerations for storing health data | Before Week 2 | Not started
Prepare a sample simulated wearable dataset (steps, heart rate, sleep) for testing | Before Week 2 | Not started

## Prathyusha
Prathyusha's tasks
Team member
Subsystem owned: | Chatbot subsystem + Mental health subsystem
Task | Due | Status
Draft functional requirements for: chat with AI assistant, get mindfulness & motivation | Before Week 2 | Not started
Research GenAI chatbot integration approach (prompt design, conversation flow) | Before Week 2 | Not started
Draft sample mindfulness exercise and motivational message content types | Before Week 2 | Not started
Write 2-3 sample chatbot conversation scenarios | Before Week 2 | Not started
Investigate safety guardrails/disclaimers needed for mental health content | Before Week 2 | Not started

## Meeting Schedule
Weekly meeting schedule
Suggested draft below — adjust days/times to match your team's real availability
Day | Time | Mode | Purpose
Wednesday | 6:00 PM | Online (Zoom/Discord) | Weekly status sync — progress, blockers, next steps
Saturday | 2:00 PM | Online or in-person | Collaborative work session / pair programming

## Leader Rotation
Team leader rotation
Assumes a 12-week term split evenly across 3 members — adjust the week ranges to match your actual term length
Weeks | Leader | Notes
Weeks 1-4 | Anthony | Current leader
Weeks 5-8 | Sakshi
Weeks 9-12 | Prathyusha

## Action Plan
Action plan — tasks before next meeting
Task | Owner | Due | Status
Review and confirm the project scope draft as a team | All | Next meeting | Not started
Review the use case and context diagrams and flag anything missing | All | Next meeting | Not started
Agree on the mobile tech stack and GenAI API | Anthony | Next meeting | Not started
Set up shared repo/workspace and communication channel | Anthony | Before Week 2 | Not started
Draft functional requirements — user management & data integration | Sakshi | Before Week 2 | Not started
Draft functional requirements — recommendation engine | Anthony | Before Week 2 | Not started
Draft functional requirements — chatbot & mental health | Prathyusha | Before Week 2 | Not started
Confirm meeting schedule with all members' real availability | All | Next meeting | Not started