## Overview
AI-Powered Personal Health Assistant
COIT20273 Capstone Project — Week 2 Team Plan
Methodology: Agile / Scrum
Sprint length: 2 weeks (except a shorter Sprint 0 for setup)
Ceremonies: Sprint planning at sprint start, weekly sync (your existing Wed meeting) doubles as stand-up, sprint review + retro at sprint end
Recommended tech stack
Layer | Choice | Why
Frontend (mobile) | React Native (Expo) | Cross-platform from one codebase; JS/TS is widely taught
Backend | Node.js + Express | Straightforward REST API; same language as the frontend
Database | PostgreSQL | Relational structure fits health data (users, goals, readings, recommendations)
Auth | Firebase Authentication | Avoids building secure auth from scratch
GenAI API | Anthropic Claude API (OpenAI as backup) | Powers chatbot, recommendations, mindfulness content
Notifications | Firebase Cloud Messaging | Free, pairs with Firebase Auth
Wearable data | Simulated dataset (JSON/CSV) | Skips OAuth/hardware complexity; real API integration is a stretch goal
Hosting | Render or Railway (free tier) | Simple deploy for Node + PostgreSQL
Version control | GitHub | Standard
Agile board | Trello | Simple, free, fits a 3-person team
Design | Figma | Wireframes before coding screens

## Requirements
Functional & non-functional requirements
Derived from the Week 1 use cases
Functional requirements
ID | Requirement | Related use case(s)
FR1 | The system shall allow users to register and manage a profile (age, weight, height, goals, dietary restrictions). | Register & manage profile
FR2 | The system shall allow users to set and update health goals. | Set health goals
FR3 | The system shall sync data from a wearable device (or simulated dataset) including steps, heart rate, sleep, and calories. | Sync wearable data
FR4 | The system shall display a health dashboard showing trends and progress over time. | View health dashboard
FR5 | The system shall generate personalised diet recommendations using GenAI based on profile and health data. | Get diet recommendation
FR6 | The system shall generate personalised exercise recommendations using GenAI based on profile and health data. | Get exercise recommendation
FR7 | The system shall provide a chatbot interface for real-time health-related Q&A. | Chat with AI assistant
FR8 | The system shall generate AI-driven mindfulness exercises tailored to user mood/progress. | Get mindfulness & motivation
FR9 | The system shall generate motivational messages based on user activity and goals. | Get mindfulness & motivation
FR10 | The system shall send notifications/reminders to users. | Cross-cutting
Non-functional requirements
ID | Category | Requirement
NFR1 | Performance | Recommendations and chatbot replies should return within ~5 seconds for good UX.
NFR2 | Security | Health data must be encrypted at rest and in transit; authentication required for access.
NFR3 | Privacy | Comply with data privacy principles; informed consent for data use; no sharing/selling of data.
NFR4 | Usability | The app must be intuitive for non-technical users; accessible UI.
NFR5 | Reliability | The app should degrade gracefully if the GenAI API is slow or unavailable (fallback message).
NFR6 | Scalability | Backend architecture should be designed to support a growing number of users.
NFR7 | Compatibility | The app should run on both Android and iOS.
NFR8 | Maintainability | Code should follow a modular architecture aligned with the subsystems.
NFR9 | Safety/ethics | Mental health content must include disclaimers and direct users to professional help where relevant — never replace professional advice.

## Software Components
Software components
Component | Description | Technology | Owner
Mobile app frontend (shell) | App shell, navigation, shared UI components | React Native (Expo) | Anthony (coordinates), all contribute
Auth & user profile module | Registration, login, profile & goals management | Firebase Auth + Node/Express + PostgreSQL | Sakshi
Wearable data integration module | Ingests simulated/real wearable data, stores readings | Node/Express API + PostgreSQL | Sakshi
Health dashboard | Visualises trends/progress from stored data | React Native + charting library | Sakshi
Recommendation engine | Generates diet/exercise plans via GenAI | Node/Express + Claude API | Anthony
Chatbot module | Real-time conversational health Q&A | Node/Express + Claude API | Prathyusha
Mental health module | Mindfulness exercises & motivational messages | Node/Express + Claude API | Prathyusha
Notification service | Sends reminders & alerts | Firebase Cloud Messaging | Anthony (shared infra)
Shared database & API gateway | Central schema & routing used by all modules | PostgreSQL + Express | Anthony (architecture), all contribute

## Documents Checklist
Documents to prepare
Document | Purpose | Owner | Status
Software Requirements Specification (SRS) | Formal record of functional & non-functional requirements | Anthony | Not started
System Design Document | Architecture, ERD, class/sequence diagrams | All (Anthony consolidates) | Not started
Project Schedule / Gantt | Timeline & milestones | Anthony | Not started
Test Plan & Test Cases | QA strategy per subsystem | All (own subsystem) | Not started
API Documentation | Endpoint reference for the backend | Sakshi (sets format), all contribute | Not started
User Manual | End-user guide | Prathyusha | Not started
Meeting Minutes Log | Record of weekly decisions | Anthony (or rotate with leadership) | Ongoing
Risk Register | Known risks & mitigations | Anthony | Not started
Final Report & Presentation | Capstone submission | All | Not started

## Tools Setup
Software tools — install & configure
Tool | Purpose | Owner | Status
VS Code | Primary IDE | All | Not started
Node.js + npm | JS runtime for backend/tooling | All | Not started
Expo CLI / React Native | Mobile app framework | All | Not started
Android Studio (emulator) | Android testing | All | Not started
PostgreSQL | Database | Sakshi | Not started
Git + GitHub repo | Version control | Anthony (sets up repo) | Not started
Postman | API testing | Sakshi | Not started
Figma | UI/UX mockups | Prathyusha | Not started
Firebase project (Auth + FCM) | Auth & notifications | Anthony | Not started
Anthropic Claude API key | GenAI integration | Anthony | Not started
Trello board | Agile task tracking | Anthony | Not started

## Task Estimates
Task time estimates
Task | Owner | Est. hours | Status
Requirements & design docs | All | 15 | Not started
Environment/tool setup | All | 8 | Not started
UI/UX wireframes (Figma) | Prathyusha | 10 | Not started
DB schema design | Sakshi | 6 | Not started
Backend API scaffolding | Anthony | 10 | Not started
Auth implementation | Sakshi | 8 | Not started
Data integration (wearable/simulated) | Sakshi | 12 | Not started
Recommendation engine (GenAI) | Anthony | 20 | Not started
Chatbot module | Prathyusha | 15 | Not started
Mental health module | Prathyusha | 12 | Not started
Notifications | Anthony | 6 | Not started
Frontend screens (all) | All | 25 | Not started
Integration & testing | All | 20 | Not started
Documentation & report writing | All | 15 | Not started
Presentation prep | All | 6 | Not started
Total |  | 188

## Task Dependencies
Task dependencies
Task | Depends on | Notes
DB schema design | Requirements finalised
Backend API scaffolding | DB schema design
Auth implementation | Backend API scaffolding
Frontend UI wireframes | Requirements finalised
Frontend screens development | Wireframes + Auth API available
Data integration module | Backend API scaffolding
Recommendation engine | Backend API + GenAI API key set up
Chatbot module | GenAI API key set up + Backend API
Mental health module | GenAI API key set up
Notifications | Backend API + Firebase setup
Integration testing | All subsystem modules complete
Documentation | Ongoing | Finalise after testing

## Project Schedule
Project schedule
Assumes a 12-week term — adjust to match your actual term length
Week | Phase / focus | Key deliverables
Week 1 | Team formation & scope | Scope doc, use case & context diagrams (done)
Week 2 | Requirements & planning | FR/NFR, components, docs list, tools, schedule (this week)
Week 3 | Design & setup (Sprint 0) | DB schema, wireframes, repo & tool setup, backend scaffolding
Week 4 | Sprint 0 wrap-up | Auth working, core API endpoints, frontend skeleton
Weeks 5-6 | Sprint 1 | Data integration + recommendation engine (diet/exercise)
Weeks 7-8 | Sprint 2 | Chatbot + mental health modules
Week 9 | Sprint 3 | Notifications + frontend polish
Week 10 | Integration testing | End-to-end testing across subsystems
Week 11 | Bug fixes & docs | Final testing, SRS/design doc finalised
Week 12 | Wrap-up | Final report, presentation, submission

## User Stories & Tasks
User stories & development tasks
Epic | User story | Points | Owner | Dev tasks
User management | As a user, I want to register and create a profile so the app can personalise my experience. | 5 | Sakshi | Design profile schema; build registration API; build registration/profile UI
User management | As a user, I want to set health goals so I can track my progress. | 3 | Sakshi | Extend schema for goals; goals API endpoint; goals UI
Data integration | As a user, I want to sync my wearable data so the app can analyse my health trends. | 8 | Sakshi | Build simulated data generator; ingestion API; sync UI
Data integration | As a user, I want to view my health dashboard so I can see my progress at a glance. | 5 | Sakshi | Aggregate queries; dashboard charts UI
Recommendation engine | As a user, I want personalised diet recommendations so I can eat healthier. | 8 | Anthony | Design GenAI prompt; API endpoint; recommendation UI
Recommendation engine | As a user, I want personalised exercise recommendations so I can train effectively. | 8 | Anthony | Design GenAI prompt; API endpoint; recommendation UI
Chatbot | As a user, I want to chat with an AI assistant so I can get real-time health advice. | 8 | Prathyusha | Chat API + GenAI integration; chat UI; conversation history storage
Mental health | As a user, I want AI-generated mindfulness exercises so I can manage stress. | 5 | Prathyusha | GenAI prompt design; API endpoint; content UI
Mental health | As a user, I want motivational messages so I stay engaged with my goals. | 3 | Prathyusha | GenAI prompt design; trigger logic; notification integration
Total points |  | 53

## Velocity Tracking
Velocity tracking
Velocity = story points your team actually completes per sprint. You can't know it before Sprint 1 finishes — use the planned points below as a starting assumption, then fill in Completed points after each sprint and the average will update automatically.
Sprint | Weeks | Planned points | Completed points | Running avg velocity | Notes
Sprint 0 | Weeks 3-4 | 8 |  | - | User management stories; mostly setup work
Sprint 1 | Weeks 5-6 | 21 |  | - | Data integration + recommendation engine (diet)
Sprint 2 | Weeks 7-8 | 16 |  | - | Recommendation engine (exercise) + chatbot
Sprint 3 | Week 9 | 8 |  | - | Mental health module + notification polish