## Overview
Name | Subsystem(s) Owned | Role | Current Status
Anthony Sutan Lie | Recommendation Engine Subsystem | Team Leader (Weeks 1–4) | Active
Sakshi Saini | User Management & Data Integration Subsystems | Team Member | Active
Prathyusha Biradar | Chatbot & Mental Health Subsystems | Team Member | Active
Objective # | Category | Description | Key Deliverable
OBJ-1 | Version Control & CM | Set up official GitHub repo, branch protection, .gitignore, and Git flow rules | Configured GitHub Repository
OBJ-2 | Assignment 1 Finalization | Complete and audit Part A (Proposal/SRS/Architecture), Part B (ILPs), and MoMs (W1–W3) | Assignment 1 Moodle Submission
OBJ-3 | Sprint 0 Technical Setup | Establish PostgreSQL/Pgvector schema, Express API server boilerplate, and Figma wireframes | Sprint 0 Baseline Architecture
OBJ-4 | Team Synchronization | Conduct Week 3 team meeting, review task dependencies, and finalize Sprint 1 backlog | Week 3 Minutes of Meeting

## Anthony Sutan Lie
Task Description | Category | Due | Status
Initialize official GitHub repository & push initial project structure | Version Control | Mid-Week 3 | In Progress
Configure GitHub branch protection on main and dev branches | Configuration Mgmt | Mid-Week 3 | In Progress
Draft and distribute Git Branching & Commit Message Guidelines to team | Team Lead | Mid-Week 3 | Completed
Scaffold Express backend API server structure & router folders | Backend Setup | End of Week 3 | In Progress
Design RAG prompt architecture and Pgvector similarity search queries | Recommendation Engine | End of Week 3 | In Progress
Audit Assignment 1 Part A (Architecture & Risk Register) and Harvard citations | Assignment 1 | Before Submission | In Progress
Chair Week 3 team meeting and finalize MoM Week 3 record | Team Lead | End of Week 3 | Completed

## Sakshi Saini
Task Description | Category | Due | Status
Define PostgreSQL database schema DDL scripts (users, health_goals, wearable_logs) | Database Setup | Mid-Week 3 | In Progress
Create .gitignore configuration for Node, Expo, and PostgreSQL credentials | Configuration Mgmt | Mid-Week 3 | Completed
Design sample JSON payload structure for simulated wearable device sync | Data Integration | End of Week 3 | In Progress
Finalize SRS requirement mapping table (FR1–FR10 & NFR1–NFR9) in Part A | Assignment 1 | Before Submission | Completed
Set up local PostgreSQL instance with Pgvector extension enabled | Environment Setup | End of Week 3 | In Progress
Write Individual Learning Plan (Part B) focusing on Database & Auth security | Assignment 1 | Before Submission | Completed

## Prathyusha Biradar
Task Description | Category | Due | Status
Create low/high-fidelity Figma wireframes for Mobile Dashboard and Chatbot UI | UI/UX Design | Mid-Week 3 | Completed
Scaffold Anthropic Claude API prompt interface handler module for Node.js | Chatbot Module | End of Week 3 | In Progress
Draft safety fallback engine logic & crisis disclaimers for mental health queries | Mental Health Module | End of Week 3 | In Progress
Compile and format final Assignment 1 document package (Part A + Part B + MoMs) | Assignment 1 | Before Submission | In Progress
Verify CQUniversity Harvard referencing list in Moodle submission draft | Assignment 1 | Before Submission | Completed
Write Individual Learning Plan (Part B) focusing on UI/UX and LLM integration | Assignment 1 | Before Submission | Completed

## Git & CM Setup
Branching Model & Codeline Standard
Branch Name | Target Codeline | Purpose / Usage | Access Policy
main | Production Baseline | Stable, deployment-ready release code | Protected (PR + 1 Approval Required)
dev | Sprint Integration Mainline | Central integration branch for active sprint | Protected (PR Required)
feature/user-mgmt/* | Feature Codeline | User registration, Auth & DB schema development | Assigned to Sakshi
feature/rec-engine/* | Feature Codeline | Recommendation engine & Pgvector pipeline | Assigned to Anthony
feature/chatbot/* | Feature Codeline | Claude API integration & UI screens | Assigned to Prathyusha
bugfix/* | Issue Hotfix | Resolving bugs identified during testing | Created as needed

## Assignment 1 Checklist
Item # | Component / Section | Details / Requirements | Owner | Audit Status
A1-01 | Part A: Group Proposal | Project Title, Executive Summary, Scope, & Subsystems | All | Verified
A1-02 | Part A: Requirements | 10 Functional (FR1–FR10) & 9 Non-Functional (NFR1–NFR9) | Sakshi | Verified
A1-03 | Part A: Architecture Design | ASCII Architecture Diagram & Pgvector RAG data flow | Anthony | Verified
A1-04 | Part A: Project Planning | WBS Package, Gantt Chart, RACI Matrix & ISO 31000 Risk Register | Prathyusha | Verified
A1-05 | Part B: Individual Learning Plan | Learning goals & skill matrix for Anthony Sutan Lie | Anthony | Completed
A1-06 | Part B: Individual Learning Plan | Learning goals & skill matrix for Sakshi Saini | Sakshi | Completed
A1-07 | Part B: Individual Learning Plan | Learning goals & skill matrix for Prathyusha Biradar | Prathyusha | Completed
A1-08 | Appendix: Meeting Minutes | Minutes of Meeting for Week 1, Week 2, and Week 3 attached | Anthony | Completed
A1-09 | Referencing Audit | CQUniversity Harvard style audit (italics for journal names/titles) | Anthony | Completed
A1-10 | Moodle Final Package | Compiled PDF document uploaded to Moodle before deadline | Prathyusha | Ready

## Action Plan
Task # | Action Description | Assigned Owner | Proposed Completion Date | Status
ACT-1 | Upload finalized Assignment 1 (Part A + B + MoMs) to Moodle | Prathyusha Biradar | 2026-07-31 | Ready
ACT-2 | Push Express API boilerplate and DB migration scripts to GitHub dev branch | Anthony / Sakshi | 2026-07-31 | In Progress
ACT-3 | Set up Trello Sprint 1 backlog board with 21 Story Points mapped | Anthony Sutan Lie | 2026-07-31 | In Progress
ACT-4 | Verify all 3 team members can clone, build, and run local Expo / Express environment | All Members | 2026-08-01 | In Progress
ACT-5 | Kick off Sprint 1 Planning Meeting (User Auth & Data Integration focus) | All Members | 2026-08-03 | Scheduled