## Overview
Name | Subsystem(s) Owned | Role | Sprint 1 Focus
Anthony Sutan Lie | Recommendation Engine Subsystem | Team Leader (Weeks 1–4) | Express API Gateway Boilerplate & RAG Controller Setup
Sakshi Saini | User Management & Data Integration Subsystems | Team Member | Firebase Auth Integration & PostgreSQL Database Schema DDL
Prathyusha Biradar | Chatbot & Mental Health Subsystems | Team Member | React Native UI Shell Navigation & Claude API SDK Interface
Week 4 / Sprint 1 High-Level Goals (Start at A11)
Goal # | Subsystem | Description | Target Deliverable
G-01 | Core Backend | Establish Express API gateway, CORS, error middleware, and database connections | Backend Express Repository
G-02 | User Management | Implement Firebase Auth registration & login endpoints and database tables | Working Auth Endpoints
G-03 | Data Integration | Write PostgreSQL DDL migration scripts (users, health_goals, wearable_logs) | DB Schema Initialized
G-04 | Frontend UI Shell | Build React Native (Expo) tab navigation (Dashboard, Chat, Profile, Recommendations) | Mobile App UI Framework
G-05 | Chatbot Service | Connect Anthropic Claude API SDK handler with backend route and basic conversation UI | Live AI Chat Baseline

## Anthony Sutan Lie
Task Description | Subsystem / Layer | Est. Hours | Status
Scaffold Express.js backend project structure, environment variables (.env), and route folders | Backend Core | 4 | Not Started
Configure PostgreSQL connection pool (pg) with pgvector extension enabled | Database Infra | 3 | Not Started
Implement centralized JSON logging and global error handling middleware | Backend Core | 2 | Not Started
Design baseline RAG context retrieval SQL queries matching user dietary/fitness constraints | Rec Engine | 5 | Not Started
Review and merge PRs from Sakshi and Prathyusha into dev branch | Team Lead / QA | 3 | Not Started
Conduct Sprint 1 Stand-up meeting and maintain Trello board status | Team Lead | 2 | Not Started

## Sakshi Saini
Task Description | Subsystem / Layer | Est. Hours | Status
Configure Firebase Admin SDK in Express backend for JWT token verification | Auth Module | 4 | Not Started
Create PostgreSQL table DDL scripts: users, health_goals, and wearable_logs | Database | 4 | Not Started
Build POST /api/v1/users/profile and GET /api/v1/users/profile endpoints | User Mgmt API | 5 | Not Started
Create simulated wearable data JSON dataset generator (steps, heart rate, sleep) | Data Integration | 4 | Not Started
Build POST /api/v1/wearable/sync ingestion endpoint | Data Integration | 4 | Not Started

## Prathyusha Biradar
Task Description | Subsystem / Layer | Est. Hours | Status
Initialize React Native Expo app with React Navigation bottom-tabs shell | Frontend App | 5 | Not Started
Build Chatbot UI screen with scrollable message list and input bar | Frontend App | 5 | Not Started
Set up Anthropic Claude API SDK handler module in backend (services/claudeService.js) | Chatbot API | 4 | Not Started
Build POST /api/v1/chat/message endpoint with system prompt safety constraints | Chatbot API | 4 | Not Started
Connect React Native Chatbot screen to Express /chat/message API endpoint | Integration | 3 | Not Started

## Sprint 1 Backlog
User Story ID | Epic / Module | User Story Statement | Story Points | Assigned Owner | Sprint Target
US-01 | User Management | As a user, I want to register and create a profile so the app can personalize my experience. | 5 | Sakshi Saini | Sprint 1
US-02 | User Management | As a user, I want to set and update my health goals (steps, sleep, weight target). | 3 | Sakshi Saini | Sprint 1
US-03 | Data Integration | As a system, I want to ingest simulated wearable logs into PostgreSQL. | 5 | Sakshi Saini | Sprint 1
US-04 | Chatbot Assistant | As a user, I want to chat with an AI assistant for real-time health and wellness advice. | 5 | Prathyusha Biradar | Sprint 1
US-05 | Core Infrastructure | As a developer, I want a unified Express API gateway with Auth verification middleware. | 3 | Anthony Sutan Lie | Sprint 1

## Action Plan
Step # | Action Item | Owner | Target Date | Status
ACT-01 | Commit Week_4_Team_Plan.xlsx and Week_4_Workshop_Solution.docx to docs/ in GitHub | Anthony Sutan Lie | 2026-08-03 | Ready
ACT-02 | Clone GitHub repo locally and create initial feature branches | All Members | 2026-08-03 | In Progress
ACT-03 | Initialize Node.js Express backend repository and push boilerplate code to dev branch | Anthony Sutan Lie | 2026-08-04 | Planned
ACT-04 | Execute PostgreSQL schema DDL and configure Firebase Auth keys | Sakshi Saini | 2026-08-05 | Planned
ACT-05 | Initialize React Native Expo app shell and connect Claude API handler | Prathyusha Biradar | 2026-08-06 | Planned